## Instructions
Action Log |  | PF/P-26:001 2026-03-06 version 1.0.1
Introduction
An effective tool for tracking commitments and actions.
• What needs to be done?
• Who is responsible for doing it?
• When does it need to be done?
• What is most important, or urgent?
• And it leaves an audit trail.
General Rules
• Shaded cells contain either a formula, or conditional formatting. Do not edit in these cells.
• The menu tab contains data used in drop-downs. You can edit them to tailor the action log for your use.
• Dates use a universal format to avoid misunderstanding. Changing the date format may stop conditional formatting working.
Action Log Columns
Title | Description | Usage
# | Unique sequence number for each action. | Extend the table by copy/pasting a complete row to maintain the formulæ and formatting.
Action / Decision | Specification of the task to be done. Tasks should be atomic - a single thing that can be completed, to avoid x% completed. Meetings also need to record decisions. | Keep them brief, but detailed enough to avoid misinterpretation.
Prio | Priority of the action, so the team can focus on what is most important. Conditional formatting helps identify the highest priorities. | Select H/M/L from the drop-down menu.
Resp | One person or title needs to be responsible for a task being accomplished (refer to RACI). | Select the person responsible from the drop-down menu.
Start Date | Records when the action was created. | Necessary to be able to calculate the handling time.
Due Date | The latest date by which this action is to be completed, helping to focus on the most urgent tasks.
Closed Date | This marks when the action was actually completed, or is agreed to be closed. | Actions may also be agreed to be abandoned.
Status | Automated status for each action, based on the date fileds, and today's date. | "Open" an action has a due date = yellow; "Due" the action was due today or earlier = red; "Closed" the action has a closed date = green.
Remark | Free text. | Extra detail for clarification, or status for progress meetings.
Menu Configuration
Table | Description | Usage
Responsible | List by name everyone in the team who might be responsible for closing actions, and reporting back to the project/meeting. | You can only assign actions to people within the team, within your control. That person might be responsible to ensure that someone outside the team performs an action.
Priority | You may redefine the symbols to denote priorities which suits your organisation. | H(igh) E(ssential) M(andatory M(edium) C(onditional) D(esirable) L(ow) O(ptional) O(ptional)

## Action Log
Action Log
| # | Action / Decision | Prio | Resp | Start Date | Due Date | Closed Date | Status | Remark
| 1 | [6 empty] | -
| 2 | [6 empty] | -
| 3 | [6 empty] | -
| 4 | [6 empty] | -
| 5 | [6 empty] | -
| 6 | [6 empty] | -
| 7 | [6 empty] | -
| 8 | [6 empty] | -
| 9 | [6 empty] | -
| 10 | [6 empty] | -
| 11 | [6 empty] | -
| 12 | [6 empty] | -
| 13 | [6 empty] | -
| 14 | [6 empty] | -
| 15 | [6 empty] | -
| 16 | [6 empty] | -
| 17 | [6 empty] | -
| 18 | [6 empty] | -
| 19 | [6 empty] | -
| 20 | [6 empty] | -
| 21 | [6 empty] | -
| 22 | [6 empty] | -
| 23 | [6 empty] | -
| 24 | [6 empty] | -
| 25 | [6 empty] | -
| 26 | [6 empty] | -
| 27 | [6 empty] | -
| 28 | [6 empty] | -
| 29 | [6 empty] | -
| 30 | [6 empty] | -
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## PF-2021 (hidden)
Date: | 2026-03-06 | Punkfrog Management
# | Initiative | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
#REF! | System admin | Purge KeepAssXC when able to drag & drop entries | L | Martin | 2020-12-14 | 2021-06-30 | 2021-02-16 | Closed
#REF! | Product | [6 empty] | -
#REF! | Sales | Convert and update brag book. | L | Martin | 2021-01-07 | 2021-06-30 | 2021-02-26 | Closed | Endorsement Wim. Latest copies. Update qualifications. Renoir, ESL, Punkfrog. Digital (index) and can print.
#REF! | Admin | Test Thunderbird - inviting to calendar meetings | H | Martin | 2020-11-16 | 2021-12-31 | 2021-12-23 | Closed | 17/10 Reported Git #275. Claims 91.0.2 fixes, but no change. | https://github.com/kewisch/gdata-provider/issues/129
#REF! | Admin | Supervise Telia cancellation & port to Hallon | M | Martin | 2021-03-27 | 2021-03-29 | 2021-03-29 | Closed | Telia subscription ends 27/3. Number ported 04:00 29/3
#REF! | Sales | Get all CV from NFT and set scope & mandate | H | Martin | 2021-01-29 | 2021-02-15 | 2021-02-12 | Closed
#REF! | HR | Profile Kristian Kjeldsen | H | Kristian | 2021-02-03 | 2021-02-28 | 2021-11-04 | Closed
#REF! | Financial | Update cashflow forecast > April | M | Martin | 2021-02-01 | 2021-03-31 | 2021-03-10 | Closed
#REF! | Financial | Start paying for balcony | H | Martin | 2020-09-15 | 2021-04-01 | 2021-02-12 | Closed
#REF! | IT | Instal Gdrive extension fix for M1 v47.0. Then revert to highest disk security. | M | Martin | 2021-02-05 | 2021-04-01 | 2021-04-23 | Closed | Seems to have come early, but not functioning. System extension for google drive needs approval. Did so many times, now not apprearing again.
#REF! | IT | VMware fusion free available for M1 | M | Martin | 2021-10-01 | 2021-12-31 | 2021-12-23 | Closed | 17/10 installed public technical review
#REF! |  | Create Insightly filter FY21/22 | M | Martin | 2021-02-12 | 2021-03-31 | 2021-02-15 | Closed
#REF! |  | Instal Ubuntu/VM | M | Martin | 2021-10-01 | 2021-12-31 | 2021-12-23 | Closed | 17/10 installed Ubuntu ARM64 preview
#REF! |  | Instal Windows 10/VM | M | Martin | 2021-10-01 | 2021-12-31 | 2021-12-23 | Closed | Wait until W10 for ARM is public download
20-1 |  | Instal Cradle 7.6 | M | Martin | 2021-10-01 | 2021-12-31 | 2021-12-23 | Closed | Cradle 7.6 is downloaded. Try Unix & W10
20-2 |  | Instal Heritage/W10 | M | Martin | 2021-10-01 | 2021-12-31 | 2021-12-23 | Closed
#REF! | HR | Create closed pond | M | Martin | 2021-03-05 | 2021-04-30 | 2021-03-18 | Closed | Only working for Pfrog
#REF! | Sales | Create profile for InterimChef based on theirs | L | Martin | 2021-03-05 | 2021-06-30 | 2021-04-22 | Closed
#REF! | Admin | Improve consultancy profile templates | H | Martin | 2021-03-18 | 2021-03-18 | 2021-03-18 | Closed
#REF! | HR | Update all profiles to new template | M | Martin | 2021-03-18 | 2021-03-31 | 2021-03-25 | Closed
#REF! | Sales | Change leads to last activity date | M | Martin | 2021-03-18 | 2021-03-31 | 2021-03-24 | Closed
#REF! | Admin | Invite Sylvana & Robert to United Spaces app | M | Martin | 2021-03-28 | 2021-04-15 | 2021-03-29 | Closed | app@unitedspaces.se or sales team.
#REF! | Admin | Change Hallon subscription 6GB after first invoice & checking that GB accumulates | M | Martin | 2021-04-30 | 2021-05-07 | 2021-04-21 | Closed
#REF! |  | Login to United Spaces app for S and E when I can log out | L | Martin | 2021-03-31 | 2021-06-30 | 2021-08-12 | Closed
#REF! | HR | Update Robin profile | M | Martin | 2021-04-01 | 2021-04-09 | 2021-04-02 | Closed
#REF! | HR | Robin Forza wrap-up | H | Martin | 2021-04-02 | 2021-04-09 | 2021-04-07 | Closed
#REF! | Quality | Survey Forza | H | Martin | 2021-04-02 | 2021-04-16 | 2021-04-07 | Closed | Response 16/4
#REF! | Sales | Complete Johan Profile | L | Martin | 2021-06-01 | 2021-07-31 | 2021-09-09 | Closed
#REF! | Sales | RabbitMQ Tuning service description | H | Martin | 2021-04-28 | 2021-04-29 | 2021-04-29 | Closed
#REF! | HR | Expense claim Emma for accommodation & train | M | Martin | 2021-05-03 | 2021-05-20 | 2021-06-30 | Closed
#REF! | Sales | Develop NOVA strategy | L | Martin | 2021-05-08 | 2021-08-31 | 2021-08-05 | Closed | They call to first meeting July
#REF! | Admin | Change Robert to Emma at UMA | M | Martin | 2021-05-20 | 2021-05-31 | 2021-05-28 | Closed
#REF! | Admin | Emma key - connect to WiFi and printer | M | Martin | 2021-05-28 | 2021-06-04 | 2021-06-03 | Closed
#REF! | Quality | Feedback: Customer services | H | Martin | 2021-06-14 | 2021-06-30 | 2021-06-16 | Closed | KJKK, Twinsite, NFT, Packlane, Betsson
#REF! | Quality | Feedback: Customer consultancy | H | Martin | 2021-06-14 | 2021-06-30 | 2021-06-16 | Closed | Cisco,Sigicom, æternity, Antigo
#REF! | Quality | Feedback: Contractors | H | Martin | 2021-06-14 | 2021-06-30 | 2021-06-16 | Closed | BRC, JW, JB, JHN, RÖ, DW, MH, NA
#REF! | Admin | Boot-up time zone and language wrong. | L | Martin | 2021-06-15 | 2021-12-31 | 2021-07-16 | Closed
#REF! | Product | Update product portfolio | M | Martin |  |  | 2021-07-19 | Closed
#REF! | Product | Create product process |  |  |  |  | 2021-07-19 | Closed
#REF! | HR | End report Daniel. Feedback, future, update profile | M | Martin | 2021-07-06 | 2021-08-15 | 2021-07-16 | Closed
#REF! | HR | End report Robin. Feedback, futire, update profile | M | Martin | 2021-07-02 | 2021-07-11 | 2021-07-16 | Closed
#REF! | Sales | Complete Jonathan profile | H | Martin | 2021-07-02 | 2021-07-11 | 2021-07-15 | Closed
#REF! | Sales | PY-NAP-ERL Concept proposal | M | Martin | 2021-09-08 | 2021-10-31 | 2021-09-16 | Closed
#REF! | Financial | Ensure SQ intangible assets specified if necessary | H | Martin | 2021-07-05 | 2021-07-20 | 2021-07-21 | Closed | Code, Documents, Source of external files, all IPR
#REF! | Financial | Article currency --> SEK on invoice - chat support | M | Martin | 2021-07-08 | 2021-07-31 | 2021-07-21 | Closed | 21/7 forum to be built
#REF! | Financial | Delay NFT payment and exploit overdraught | M | Martin |  |  | 2021-10-14 | Closed
#REF! | Financial | TVV Avstämning | H | Martin | 2021-09-24 | 2021-10-20 | 2021-10-08 | Closed | Fredrik says can apply few more months samtidigt.
#REF! | Financial | SQ bankruptcy ruling | H |  |  | 2021-08-10 | 2021-09-16 | Closed | Waiting for letter from tingsrätten
#REF! | Financial | If need personal loan, assign to 2893 |  |  |  |  | 2021-09-15 | Closed
#REF! | Operations | Get fullmakt from NFA to run WokforceLogIQ | H | 2021-07-08 | 2021-07-09 | 2021-07-16 | 2021-08-10 | Closed | Reminded & updated 19/7
#REF! | Sales | Agreement with NFA to act as VP Sales | H | 2021-07-08 | 2021-07-09 | 2021-07-16 | 2021-08-03 | Closed | Reminded & updated 19/7
#REF! | Sales | Update Daniel profile | H | Martin | 2021-07-12 | 2021-07-31 | 2021-08-10 | Closed
#REF! | Sales | Update Robin profile | L | Robin | 2021-07-14 | 2021-10-31 | 2021-12-09 | Closed | Share file & remind
#REF! | Sales | Update Per's profile in WFQ/VMS | L | Martin | 2021-09-01 | 2021-09-30 | 2021-07-20 | Closed
#REF! | Quality | Packlane survey | L | Martin | 2021-07-16 | 2021-07-31 | 2021-09-09 | Closed | Withdraw
#REF! | Admin | Look for cheaper office space | M | Martin | 2021-08-01 | 2021-10-01 | 2021-08-12 | Closed
#REF! | Financial | Activate WISE account, when needed for OS TX | L | Martin | 2021-08-01 | 2021-12-31 | 2021-08-26 | Closed
#REF! |  | Design Effective Meetings workshop | L | Martin |  | 2021-09-09 | 2021-09-09 | Closed | Deliver to Emma & Alice
#REF! |  | Implement EM wshop for Emma & Alice | L |  |  | 2021-09-09 | 2021-09-09 | Closed
#REF! |  | Create certificate of completion | L |  |  | 2021-09-09 | 2021-09-09 | Closed
#REF! | Sales | Update Niclas profile | H |  |  |  | 2021-08-16 | Closed
#REF! | Admin | Print refills - 2022-2027 | M | Martin | 2021-08-18 | 2021-10-30 | 2021-09-09 | Closed
#REF! | Security | Purge all ownit email accounts & services | H | Martin | 2021-08-16 | 2021-08-20 | 2021-08-18 | Closed | ManageBac, OpenApply, SAS, Custodian, Mercer, MLC
#REF! | Security | Migrate ownit emails | H | Martin | 2021-08-18 | 2021-08-20 | 2021-08-20 | Closed
#REF! | Security | Shout down ownit email account | H | Martin | 2021-08-18 | 2021-08-20 | 2021-08-20 | Closed
#REF! | Sales | Get Antigo signed by Fredrik | L | Martin | 2021-08-16 | 2021-08-26 | 2021-08-30 | Closed
#REF! | Admin | Get TMI refills from Ulf | L |  |  | 2021-11-11 | 2021-11-11 | Closed
#REF! | Sales | SkillfindR S3 - pricing (esp. tool) | H | Martin | 2021-08-30 | 2021-09-05 | 2021-09-30 | Closed
#REF! | Financial | Repay KJK from UMA deposit refund 2x20.000 | H | Martin | 2021-10-15 | 2022-01-31 | 2021-12-22 | Closed | Nordea clr 3300 acct 800209-0416
#REF! | Admin | Hole punch delivered | H | Amazon | 2021-09-25 | 2021-10-13 | 2021-10-14 | Closed | Before I move …
#REF! | Security | Identify paycards in use och minimise |  | Martin | 2021-10-01 | 2021-10-31 | 2021-10-17 | Closed
#REF! | Financial | Appeal against TVV decision | H | Martin | 2021-10-05 | 2021-10-06 | 2021-10-06 | Closed
#REF! | Financial | Apply for tax deferral | H | Martin | 2021-10-06 | 2021-10-10 | 2021-10-10 | Closed
#REF! | Sales | Claim EIR commission when contract signed | H | Per | 2021-10-09 | 2021-10-15 | 2021-11-22 | Closed | 12/11 Silence two weeks
#REF! | Sales | Trust US network in NordVPN | H | Martin | 2021-10-15 | 2021-11-03 | 2021-10-21 | Closed
#REF! | Sales | Trust Regus network in NordVPN | H | Martin | 2021-10-15 | 2021-11-03 | 2021-11-04 | Closed
#REF! | Financial | Stop paying union? | M | Martin | 2021-10-11 | 2021-12-31 | 2021-12-15 | Closed | Union tied to Bliwa
#REF! | Strategy | Risk-sharing for consultants. List tasks + effort + value, payback if nit assignment 3-6 months | H | Martin | 2021-10-28 | 2021-12-14 | 2021-12-09 | Closed
#REF! | Strategy | Contract outline, risk-sharing awlays revenue for my services (RabbitMQ, NOVA, PNE) | H | Martin | 2021-10-28 | 2021-12-14 | 2021-12-09 | Closed
#REF! | Financial | Ask for donations for walk-aways (Johan, Niclas) | H | Martin | 2021-10-28 | 2021-12-14 | 2021-12-09 | Closed
#REF! | Strategy | Sketch exit strategy | H | Martin | 2021-10-28 | 2021-12-14 | 2021-12-09 | Closed
#REF! | Financial | Plan to repay deferred taxes | H | Martin | 2021-10-28 | 2021-12-14 | 2021-12-09 | Closed
#REF! | Admin | Order printer Brother MFC-L3770 CDW & toner | L | Martin | 2021-11-01 | 2021-11-07 | 2021-11-25 | Closed | When need arises
#REF! | Admin | Building code didn't work | H | Martin | 2021-10-31 | 2021-11-01 | 2021-11-07 | Closed | Test again when bring chair Saturday
#REF! | Admin | Rubbish bin | H | Martin | 2021-10-31 | 2021-11-05 | 2021-11-05 | Closed
#REF! |  | Add MBSE to my CV | L |  |  |  | 2021-11-11 | Closed
#REF! |  | Delete Amazon.com account | L | Martin | 2021-11-30 | 2021-12-31 | 2021-12-02 | Closed | Wait until refund resolved
#REF! | Sales | dosR pitch | H | Martin | 2021-11-25 | 2021-12-14 | 2021-12-14 | Closed | To see if Ulf wants to support
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## B-2020 (hidden)
Date: | 2026-03-06 22:50
# | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | Investigate the non-competition clause at ESL towards their customers | M | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed | Non-compete/solicit customers/staff before 25/10, if I had dealings with them after 2018-04-27. All clear now customers & staff.
2 | Decision: Throw some business towards ESL | L | Martin | 2019-08-28 | 2019-08-28 | 2019-08-28 | Closed | Have offered with ancillary service like certification but pricing not agreed.
3 | Review 2019 budget | M | Ulf | 2019-08-28 | 2020-04-30 | 2020-03-25 | Closed | Do for 2020 instead
4 | Share budget template with Nordforce | L | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed
5 | Set revenue assurance goals for 1/1 | H | Martin | 2019-08-28 | 2019-09-30 | 2019-08-28 | Closed | MC 50% (which) + RG + 1-3 subcon
6 | Call next meeting Friday 13th Dec | M | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed | Moved to 18/12
7 | Meeting template: make strategy larger; add miletone plan to show overview status V plan | M | Martin | 2019-08-28 | 2019-11-30 | 2019-08-28 | Closed
8 | Lower profit at EOFY | M | Martin | 2019-12-18 | 2020-02-15 | 2020-03-06 | Closed | Balance IOU with overdraught
9 | Sell Marcus and Alex from NFT | M | Martin | 2019-12-18 | 2020-03-31 | 2020-03-15 | Closed | Klarna
10 | Postpone private loan as long as possible | H | Martin | 2019-12-18 | 2020-01-15 | 2020-01-01 | Closed | Took overdraught instead initially.
11 | Develop service products during Xmas break | H | Martin | 2019-12-18 | 2020-01-15 | 2020-01-07 | Closed | Mapped a complete portfolio. Implemented CI-7MT. Identified EffMeet, Metrics.
12 | Produce balance sheet and P/L statement in Swedish | M | Martin | 2020-03-25 | 2020-06-17 | 2020-05-21 | Closed
13 | At AGM, "The board of directors of Punkfrog AB proposes that the annual general meeting authorises the Board of Directors to, on one or several occasions , prior to the next annual general meeting, with or without deviating from the shareholders' preferential rights - resolve to issue new shares." | M | Ulf | 2020-03-25 | 2020-10-06 | 2020-05-21 | Closed
14 | Place copies of reference documents into meeting folder, as some members do not have access to other folders via links | M | Martin | 2020-06-04 | 2020-06-06 | 2020-06-05 | Closed
15 | Add Payroll tax components to liquidity forecast | H | Martin | 2020-06-04 | 2020-06-06 | 2020-06-05 | Closed
16 | If the tax return causes liquidity problems, consider taking a loan from the Tax Account | M | Martin | 2020-09-17 | 2021-01-31 | 2021-04-13 | Closed | Will do if necessary
17 | Find out when tax payment is due | H | Martin | 2020-09-17 | 2020-09-25 | 2020-09-21 | Closed | 90 days after decision from SV. Probably 2021-03-21.
18 | Sell Seeqest shares to pay the tax bill. Monitor closely in case losses reduce capital below 50%. | M | Martin | 2020-09-17 | 2021-01-21 | 2020-12-11 | Closed | 5/10 Yrev says not a risk. Working on ways to recover assets.
19 | Call meeeting of Seeqest shareholders to sanitise the finances | M | Martin | 2020-09-17 | 2020-12-18 | 2020-11-24 | Closed | NFT+PF+[Lennart ¦ Jokla]. If October invoice unpaid.
20 | Which agents already have Marcus' CV (to avoid a clash)? | H | Martin | 2020-09-17 | 2020-09-21 | 2020-09-18 | Closed | No fresh ones. Keep aligned.
21 | Terminate UMA office | H | Martin | 2020-09-17 | 2020-09-30 | 2020-12-13 | Closed | Will do if necessary
22 | Move into home office | L | Martin | 2020-09-17 | 2020-11-30 | 2020-12-13 | Closed | Connected to previous
23 | Focus sales on current consultants: Robin, Marcus, Jonas, Brett. | H | Martin | 2020-09-17 | 2020-10-31 | 2020-11-20 | Closed | Added Daniel, Benjamin
24 | Lower rate for Martin 800-900 | H | Martin | 2020-09-17 | 2020-09-30 | 2020-10-15 | Closed | Marketing ploy - no management overhead, lean company
25 | Meet Tingent to discuss my profile and rate | H | Martin | 2020-09-17 | 2020-09-25 | 2020-09-24 | Closed
26 | Approach ETM under 1000, then apply for TVV checkar för internationalisering. | H | Martin | 2020-09-17 | 2020-09-30 | 2020-09-23 | Closed | Could begin with 950, then revert to 1200*50%
27 | Investigate if the Tax Account loan (see point 16) is a time-limited offer | H | Martin | 2020-12-18 | 2020-12-31 | 2021-04-13 | Closed
28 | [6 empty] | -
29 | [6 empty] | -
30 | [6 empty] | -
31 | [6 empty] | -
32 | [6 empty] | -
33 | [6 empty] | -
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## B-2019 (hidden)
Date: | 2026-03-06 22:50
# | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | Investigate the non-competition clause at ESL towards their customers | M | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed | Non-compete/solicit customers/staff before 25/10, if I had dealings with them after 2018-04-27. All clear now customers & staff.
2 | Decision: Throw some business towards ESL | L | Martin | 2019-08-28 | 2019-08-28 | 2019-08-28 | Closed | Have offered with ancillary service like certification but pricing not agreed.
3 | Review 2019 budget | M | Ulf | 2019-08-28 | 2019-11-30 |  | Due
4 | Share budget template with Nordforce | L | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed
5 | Set revenue assurance goals for 1/1 | H | Martin | 2019-08-28 | 2019-09-30 | 2019-08-28 | Closed | MC 50% (which) + RG + 1-3 subcon
6 | Call next meeting Friday 13th Dec | M | Martin | 2019-08-28 | 2019-08-30 | 2019-08-28 | Closed | Moved to 18/12
7 | Meeting template: make strategy larger; add miletone plan to show overview status V plan | M | Martin | 2019-08-28 | 2019-11-30 | 2019-08-28 | Closed
8 | Lower profit at EOFY | M | Martin | 2019-12-18 | 2020-02-15 |  | Due | Tactics with Y revision
9 | Sell Marcus and Alex from NFT | M | Martin | 2019-12-18 |  |  | - | Availability & profiles
10 | Postpone private loan as long as possible | H | Martin | 2019-12-18 | 2020-01-15 |  | Due | Take second loan if necessary
11 | Develop service products during Xmas break | H | Martin | 2019-12-18 | 2020-01-15 |  | Due | RCA, Meetings, mEdison spec, spec for PF training & tuning services
12 | [6 empty] | -
13 | [6 empty] | -
14 | [6 empty] | -
15 | [6 empty] | -
16 | [6 empty] | -
17 | [6 empty] | -
18 | [6 empty] | -
19 | [6 empty] | -
20 | [6 empty] | -
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## PF-2022 (hidden)
Date: | 2026-03-06 | Punkfrog Management
# | Initiative | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | Sales | Invoice EIR | H | Martin | 2022-01-10 | 2022-01-10 | 2022-01-10 | Closed | Start date. 90Kx1.25
2 | Marketing | PNE article for Elektronik | L | Martin | 2021-12-01 | 2022-02-28 |  | Due
3 | Marketing | Document EIR journey (proof of concept) | L | Martin | 2022-01-10 | 2022-07-10 |  | Due
4 | Marketing | Endorsement from Per | L | Martin | 2022-01-10 | 2022-07-10 |  | Due
5 | Financial | Repay KJK 10.000 | L | Martin | 2022-01-20 | 2022-01-25 | 2022-01-20 | Closed | Nordea clr 3300 acct 800209-0416
6 | IT | Test Tbird - inviting to calendar meetings - Git #275 | L | Martin | 2020-10-17 | 2021-12-31 | 2022-02-24 | Closed | 25/1 Not fixed in new release. New issue report. | https://github.com/kewisch/gdata-provider/issues/129
7 | IT | VMware fusion free available for M1 | L | Martin | 2021-10-01 | 2021-12-31 | 2022-03-06 | Closed | Parallels 17
8 | IT | Instal Ubuntu/VM | L | Martin | 2021-10-01 | 2021-12-31 | 2022-03-06 | Closed | 17/10 installed Ubuntu ARM64 preview
9 | IT | Instal Windows 10/VM | L | Martin | 2021-10-01 | 2021-12-31 | 2022-03-06 | Closed | Wait until W10 for ARM is public download
10 | IT | Instal Cradle 7.6 | L | Martin | 2021-10-01 | 2021-12-31 | 2022-03-07 | Closed | Cradle 7.6 is downloaded. Try Unix & W10
11 | IT | Instal Heritage/W10 | L | Martin | 2021-10-01 | 2021-12-31 | 2022-03-06 | Closed
12 | Marketing | Ask venues when ready to have meetups | M | Martin | 2022-01-10 | 2022-06-30 | 2022-10-13 | Closed
13 | Delivery | RMQ Operations structure & templates | H | Martin | 2022-02-01 | 2022-07-01 | 2022-06-15 | Closed | Shared drive, survey, log << Betsson sign
14 | Strategy | Goals 2022: TMI | L | Martin | 2022-01-01 | 2022-01-31 |  | Due
15 | Delivery | Read IIBA Agile & document techniques | L | Martin | 2022-01-01 | 2022-01-31 |  | Due
16 | Marketing | Staff shirts printing for Code BEAM STO | H | Martin | 2022-03-01 | 2022-05-18 | 2022-04-13 | Closed
17 | Marketing | Create website | M | Martin | 2022-01-10 | 2022-08-31 |  | Due | Webflow
18 | Marketing | Content for website & linkedin | L | Martin | 2022-01-10 | 2022-10-30 |  | Due | Based on my generic template. Using 11ty?
19 | Dev | Clean up git and github - one location. Not public? | L | Martin | 2022-01-10 | 2022-08-31 |  | Due | Martin/Development/flutter /Documents/Punkfrog/Dev/dosR/ /local-dev/punkfrogab.github.io
20 | Product | Revive dosR to build for Test Flight | L | Volkan | 2021-01-29 | 2022-08-31 |  | Due | Pay someone to teach me how :) Move loccal
21 | Admin | Update Office Handbook | H | Martin | 2021-12-01 | 2022-01-09 | 2021-12-20 | Closed
22 | Sales | Get photo for Brett's bio | L | Brett | 2021-12-20 | 2022-01-15 | 2022-01-15 | Closed
23 | Financial | Report theft to police 9/2 14:15 Götg 92 |  |  |  |  | 2022-02-17 | Closed | I-53-16444 000 44630
24 | Financial | Court of appeal decision |  |  |  |  | 2022-02-17 | Closed | $Moodoom1 to read
25 |  | Add/transfer Applecare 5637573190 to laptop |  |  |  | 2022-02-26 | 2022-02-28 | Closed
26 |  | Add Applecare to iPhone |  |  |  | 2022-02-26 | 2022-02-28 | Closed
27 |  | Elgiganten delivery> fodral+JBL+pbank |  |  | 2022-02-18 | 2022-02-22 | 2022-02-21 | Closed
28 |  | Dustin invoice: Satechi pro hub+fodral |  |  | 2022-02-18 |  | 2022-02-21 | Closed
29 |  | Delivery planner | H |  | 2022-02-18 | 2022-05-03 | 2022-03-30 | Closed
30 |  | Delivery TUMI bag: Tariq Folkungag. 61 |  |  | 2022-02-18 |  | 2022-02-23 | Closed
31 |  | Delivery Nimalist wallet | H |  | 2022-02-18 | 2022-03-31 | 2022-05-05 | Closed | Refund by 12/4, then troll
32 | Sales | Negotitae sttlement with Johan about DD, before contacting Fredrik | H | Martin | 2022-03-03 | 2022-08-19 | 2022-08-18 | Closed | 10% commission everything, via Punkfrog. Trust for PNE, RabbitMQ
33 | Financial | Finalise budget proposal | M | Martin | 2022-05-10 | 2022-05-10 | 2022-05-11 | Closed | Get Fredrik to move balance sheet to budget
34 | Sales | Finalise Business plan | M | Martin | 2022-05-10 | 2022-05-10 | 2022-05-11 | Closed | Needs final budget
35 | Sales | Negotiate or cancel VP Sales at NFA | H | Martin | 2022-03-06 | 2022-03-16 | 2022-03-31 | Closed
36 | Financial | TVV to Court of Appeals | H | TVV | 2022-02-17 | 2022-09-30 | 2022-09-15 | Closed | Ruled for TVV, brought Torbjörn in.
37 | Product | Configure cradle and define dosR project | L | Martin | 2022-03-07 | 2022-04-30 |  | Due | Only 60 day licence for Windows 11. Downgrade to W10?
38 | Financial | Extend anstånd 14/3 - 10/10 | H | Martin | 2022-03-08 | 2022-03-14 | 2022-03-15 | Closed
39 | Financial | Stämma av TVV 2021 after 2020 decision | H | Martin | 2022-03-10 | 2022-04-06 | 2022-04-05 | Closed
40 | dosR | Create input requirements dosR | H | Martin | 2022-03-01 | 2022-03-31 |  | Due
41 | dosR | Capture requirements in Cradle | H | Martin | 2022-03-01 | 2022-03-31 |  | Due
42 | dosrR | DFD | L |  |  |  |  | -
43 | dosr | ERD | L |  |  |  |  | -
44 | dosr | STD | L |  |  |  |  | -
45 | dosr | Connect requirements to models | L |  |  |  |  | -
46 | Sales | Replace clicker with good one | M | Martin | 2022-03-15 | 2022-03-31 | 2022-03-21 | Closed
47 |  | Spare multi-charging cables | M | Martin | 2022-03-24 | 2022-03-31 | 2022-03-29 | Closed | One frayed: EPZ1, Nördic, Baseus
48 | Product | Rip 5.25" diskettes in London | L | Martin | 2022-04-01 | 2022-04-30 |  | Due
49 | Marketing | Contact Calle when he is VD Sigicom | L | Martin |  |  | 2022-10-13 | Closed
50 | Finance | Claim PF Biz refund | H | Martin | 2022-02-21 | 2022-06-09 | 2022-06-09 | Closed | 18/5 submitted again
51 |  | Mina cobol SEB, Herbert Daly | [5 empty] | -
52 |  | Peter Lund BLU (asking for ESL?) | L | Martin | 2022-05-20 | 2022-05-31 | 2022-05-21 | Closed
53 | Marketing | Meetup pipeline = speakers | H | Martin | 2022-05-22 | 2022-06-30 | 2022-10-14 | Closed
54 | Finance | Get pricing for Visma Tid Smart/Pro | M | Martin | 2022-05-23 | 2023-05-31 | 2022-06-01 | Closed | Ring 0470 70 61 00
55 | Financial | TVV 2021 komplettering | H | Martin | 2022-06-10 | 2022-06-24 | 2022-07-03 | Closed | Repay decision. Appealed to Court of Appeals 29/6
56 | Financial | TVV 2021 addition to appeals court | H | Martin | 2022-07-01 | 2022-07-22 | 2022-07-13 | Closed
57 | Financial | Renew pynaperl domains | M | Martin | 2022-08-01 | 2022-09-08 | 2022-07-20 | Closed
58 | Catering | Take inventory, label, and complement | M | Martin | 2022-08-01 | 2022-09-30 | 2022-10-10 | Closed | Chafing containers, spoons & holders,
59 | Catering | Store in basement | M | Martin | 2022-08-01 | 2022-08-31 | 2022-10-10 | Closed
60 | Catering | Register trading name | M | Martin | 2022-09-01 | 2022-09-30 | 2022-09-23 | Closed
61 | Catering | Create logo and labels | L |  |  |  |  | -
62 | Catering | Pricing model | [5 empty] | - | Rental based on Storköksbutiken
63 | Financial | Do extra AGM to register MT Revision as auditor | L | Martin | 2023-01-15 | 2022-09-12 | 2022-09-12 | Closed
64 | Financial | Defer pensions until Jan 2024 | L | Martin | 2022-11-01 | 2022-12-15 | 2022-11-11 | Closed
65 | Product | PNE website | [5 empty] | -
66 | Product | PNE logo | [5 empty] | -
67 | HR | Modify employments contracts and template to comply with EU directive 2019/1152 | L | Martin |  |  |  | -
68 | Product | Get NDA at Happi Hacking prior to collaboration | L | Martin | 2022-09-19 | 2022-09-30 |  | Due
69 | Admin | Convert Emma's hallon subscription to private | H | Martin | 2022-09-24 | 2022-09-30 | 2022-10-01 | Closed | 1. Private SIM new num 2. When SIM move in chat
70 | Sales | Get testimonial from Betsson during survey | H | Martin | 2022-11-15 | 2022-12-15 |  | Due
71 | Sales | Create SAFEe bio for me | H | Martin | 2022-10-05 | 2022-10-15 |  | Due | Sprints CHINA. LEAN Reboir x3.
72 | Financial | Create separate profit centre for Celebes | L | Martin | 2022-10-10 | 2023-03-31 |  | Due | First revenue
73 | Marketing | Ask for hosts | M | Martin | 2022-10-10 | 2022-10-14 | 2022-10-14 | Closed
74 | Marketing | Ask for speakers | M | Martin | 2022-10-10 | 2022-10-14 | 2022-10-14 | Closed
75 | Marketing | Create youtube channel | H | Martin | 2022-10-10 |  |  | -
76 | Admin | How get images in Thunderbird footers | M | Martin | 2022-10-10 | 2022-12-31 | 2022-10-28 | Closed | Create by write email then save as HTML
77 | HR | Split RMQ Advisory into Frame plus WO | M | Martin | 2022-10-01 | 2022-10-31 | 10/310 | Closed | 11/10 In review
78 | Sales | Replace Betsson advisory with Frame plus WO | M | Martin | 2022-10-11 | 2022-10-31 | 2022-10-20 | Closed
79 | Business | Ensure 62 is primary area of business not 70. | L | Martin | 2022-10-14 | 2022-12-31 | 2022-10-20 | Closed | 14/10 asked branschvinnarna how
80 | Admin | All templates doc no. & neutral footer | L | Martin | 2022-10-24 | 2022-12-31 |  | Due
81 | Sales | CSP documents S3, 2, 5 | L | Martin | 2022-11-14 | 2022-12-31 |  | Due | No hurry unless HH want to buy
82 |  | Develop Erlang arguments and PNE | H | Martin | 2022-11-14 | 2022-12-31 |  | Due | Johan > Robert
83 |  | Book next 6 months Betsson monthly meetings | L | Martin | 2022-11-15 | 2023-06-01 | 2022-11-25 | Closed
84 | Marketing | Buy Kahoot Pro €468 or Priv €225 | L | Martin | 2022-11-30 | 2023-01-31 |  | Due | Personal: Basic 10, Home 20, Family 20, Premier 50.
85 | Marketing | Confirm host for next meetup | H | Martin | 2022-12-10 | 2022-12-31 |  | Due | Alexander Klarna back 14/1
86 | Sales | Teracloud Frame Agreement | H | Martin | 2022-12-10 | 2022-12-31 |  | Due | Johan 29/12
87 | Sales | Pitch Xperi ++ | H | Martin | 2022-12-10 | 2022-12-31 | 2022-12-30 | Closed | Paul 29/12
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## uma2regus (hidden)
| Terminate at United Spaces | 2021-08-12
Sign at Regus
Date: | 2026-03-06 | Change Office
# | Timing | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | Before | Terminate at United Spaces | H | Martin | 2021-08-12 | 2021-08-13 | 2021-08-12 | Closed | Last contractual day 31/10
2 | Before | Sign ageement at Regus | H | Martin | 2021-08-12 | 2021-08-13 | 2021-08-16 | Closed | Notified 12/8. Room 913, 7% discount, 2 years, start date 1/11
3 | Before | Agree on date to move out/in | H | Martin | 2021-08-12 | 2021-10-31 | 2021-09-24 | Closed | Friday 29/10 OUT/IN
4 | Move | Pay 2 months deposit + 1 month rent | H | Martin | 2021-09-01 | 2021-11-01 | 2021-08-30 | Closed | Pay early to trigger order for furniture
5 | After | Get deposit returned | M | US | 2021-11-01 | 2021-11-30 | 2021-10-25 | Closed | There was no deposit. It was 2 months in advance.
6 | Move | Move contents to new office & white table home | H | Martin | 2021-10-31 | 2021-10-31 | 2021-10-29 | Closed | Move Alice same time? Things to tip?
7 | Before | Decide office furnishing | H | Martin | 2021-08-13 | 2021-08-20 | 2021-08-16 | Closed | Use layout diagram
8 | After | Update budget | L | Martin | 2021-11-01 | 2021-11-30 | 2021-10-14 | Closed
9 | Before | Change Google Business Address | M | Martin | 2021-10-01 | 2021-10-31 | 2021-09-30 | Closed | https://business.google.com/edit/l/00944347174387892497?trk=https%3A%2F%2Fnotifications.google.com%2Fg%2Fp%2FAD-FnExf-EgikZ5yqcXmNxmdMDPnscCGq6NgB1ufMxxBS871EAVT2dxfuLP-PTM2Ni4XKta43juNqgq0wcoZjuM
10 | Before | Get new rubber stamp with address | L | Martin | 2021-11-01 | 2021-12-31 | 2021-10-14 | Closed | 1/10 ordered
11 | Before | Change address BV, adressändring for myndigeter | M | Martin | 2021-10-01 | 2021-10-31 | 2021-09-30 | Closed | verksamt.se eTjänsten
12 | After | Change footers & addresses on all templates | M | Martin | 2021-10-15 | 2021-11-01 | 2021-09-30 | Closed
13 | After | Update Office Handbook | H | Martin | 2021-11-01 | 2021-11-07 | 2021-11-04 | Closed
14 | After | Order printer Brother MFC-L3770 CDW & toner | L | Martin | 2021-11-01 | 2021-11-07 | 2021-11-04 | Closed | When need arises
15 | After | Notify all vendors | M | Martin | 2021-10-15 | 2021-11-01 | 2021-10-01 | Closed
16 | After | Notify all customers | L | Martin | 2021-11-01 | 2021-11-30 | 2021-11-04 | Closed | Not really important unless stated in contract.
17 | After | Notify all partners | M | Martin | 2021-11-01 | 2021-11-30 | 2021-10-01 | Closed
18 | After | Check allabolag.se has address | L | Martin | 2021-11-01 | 2021-12-31 | 2021-10-31 | Closed | BV changed 1/10
19 | Before | Gereate & validate refills | H | Martin | 2021-09-01 | 2021-09-30 | 2021-08-30 | Closed
20 | Before | Print refills | L | Martin | 2021-09-01 | 2021-10-30 | 2021-10-31 | Closed | 2022, 2023 OK. 2024, 2025, 2026, 2027.
21 | Before | Order removal van | H | Martin | 2021-10-01 | 2021-10-15 | 2021-09-27 | Closed | 495:-Litet Ford Transit. Lastkaj Skansbrogatan 5.
22 | Before | Check if large items fit in lift | H | Martin | 2021-09-16 | 2021-09-30 | 2021-09-18 | Closed
23 | Before | Get keys from Emma and Sylvana | H | Martin | 2021-09-22 | 2021-10-29 | 2021-10-29 | Closed | Sylvana 27/9
24 | Before | Svenskadressändring | M | Martin | 2021-09-30 | 2021-10-15 | 2021-10-15 | Closed
25 | After | Check old postbox | M | Martin | 2021-10-29 | 2021-12-31 | 2021-11-04 | Closed | Ask Hanan
26 | After | Return flyttkartong & MC key | H | Martin | 2021-10-31 | 2021-11-01 | 2021-11-02 | Closed
27 | After | Move printer to office, if allowed? | H | Martin | 2021-10-31 | 2021-11-30 | 2021-11-01 | Closed
28 | After | Write procedure for removals | M | Martin | 2021-10-31 | 2021-11-07 | 2021-11-04 | Closed
29 | After | Building code didn't work | H | Martin | 2021-10-31 | 2021-11-01 | 2021-11-04 | Closed | Test again when bring chair Saturday
30 | After | Take rubbish to recycling | H | Martin | 2021-10-31 | 2021-11-01 | 2021-11-01 | Closed
31 | After | How does cabinet lock? | H | Martin | 2021-10-31 | 2021-11-05 | 2021-11-03 | Closed
32 | After | Adjust chair | H | Martin | 2021-10-31 | 2021-11-05 | 2021-11-04 | Closed
33 | After | Rubbish bin | H | Martin | 2021-10-31 | 2021-11-05 | 2021-11-04 | Closed
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## Menu
Responsible | Remark
Fred
Sarah
CTO
VP Sales
Priority | Remark
H | High = red.
M | Medium = yellow.
L | Low = white.

## PF-2019 (hidden)
Date: | 2026-03-06 22:50 | Punkfrog Management
# | Initiative | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | IT | Select doc package | H | Martin | 2019-02-10 | 2019-02-15 | 2019-02-12 | Closed | Gdocs --> MS Office 360
2 | IT | Select domain name .io .se .eu | H | Martin | 2019-02-10 | 2019-02-15 | 2019-01-12 | Closed | .se
3 | IT | Create Gdrive, email for punkfrog.se | H | Robert | 2019-02-10 | 2019-02-28 | 2019-02-25 | Closed
4 | IT | Select financial system | H | Martin | 2019-02-10 | 2019-03-31 | 2019-03-11 | Closed | Trial Visma and Fortnox
5 | Legal | Stiftelse urkund, Bolagsordning | H | Martin | 2019-02-10 | 2019-02-13 | 2019-02-10 | Closed | verksamt.se
6 | Financial | Open bank account for punkfrog | H | Martin | 2019-02-10 | 2019-02-11 | 2019-02-13 | Closed | Bmeet at bank 10-18 08 4520000 Fpaket 1250/yr
7 | Financial | Deposit 50.000 captial | H | Martin | 2019-02-10 | 2019-02-11 | 2019-02-13 | Closed | Need payment from ESL
8 | ` | Get bankintyg from SHB | H | Martin | 2019-02-10 | 2019-02-13 | 2015-02-01 | Closed
9 | Legal | Register with BV (SU, BO, BI, 1900) | H | Martin | 2019-02-10 | 2019-02-13 | 2015-02-01 | Closed
10 | Legal | Get business registration | M | BV | 2019-02-12 | 2019-03-15 | 2021-02-01 | Closed | Org.nr 25 days (start 13/2). Meet at bank to close deal.
11 | Financial | Finalise banking & talk insurance | H | Martin | 2019-02-13 | 2019-02-25 | 2019-02-25 | Closed
12 | Financial | Create company binders | L | Ylva | 2019-03-27 | 2019-03-31 | 2019-03-27 | Closed | Which to keep on paper?
13 | Financial | Get Liability Insurance | H | Camilla | 2019-02-10 | 2019-04-30 | 2019-05-18 | Closed
14 | Legal | Create Aktiebok | L | Martin | 2019-02-10 | 2019-03-31 | 2019-07-07 | Closed | Must be kept for public access
15 | Financial | Ansök f-skatt och MOMS registrering hos Skatteverket | H | Martin | 2021-02-01 | 2024-02-01 | 2019-02-24 | Closed | Estimate 300.000
16 | Financial | Betala in preliminär skatt (f-dskatt) | H | Ylva | 2019-03-27 | 2019-08-12 | 2019-05-08 | Closed | Got 3 months uppskov
17 | Financial | Upprätta bokföring | H | Ylva | 2019-03-27 | 2019-04-16 | 2019-05-08 | Closed
18 | Financial | VAT nr från Skattevverket | M | Ylva | 2019-03-27 |  | 2019-05-08 | Closed | handel inom EU. (get with MOMS) Is it separte?
19 | Sales | Create invoice template | M | Martin | 2019-02-10 | 2019-03-01 | 2019-02-23 | Closed | Adapt Redfin
20 | Legal | Sign consulting contract with ESL | H | Martin | 2019-02-10 | 2019-02-11 | 2019-02-13 | Closed
21 | Legal | Terminate employment at ESL | H | Martin | 2019-02-10 | 2019-02-11 | 2019-02-13 | Closed | Expected end date 31/3
22 | Marketing | Creat logo and style guide | M | Martin | 2019-01-18 | 2019-03-31 | 2019-04-30 | Closed | Dark green?
23 | Marketing | Create document basic templates | L | Martin | 2019-02-10 | 2019-03-31 | 2019-05-08 | Closed | Change to dark green?
24 | Marketing | Create website | L | Set | 2019-05-01 | 2019-12-31 | 2019-12-20 | Closed | Cancelled
25 | Legal | Transfer MD liability to Stuart via BV | H | Martin | 2019-02-10 | 2019-02-28 | 2019-04-01 | Closed | BV takes 20 work days to change bolagsman
26 | Administration | Notify ESL that I have resigned | H | Martin | 2019-02-28 | 2019-03-31 | 2019-03-28 | Closed | E-day 7/3
27 | Financial | Buy phone | H | Martin | 2019-03-15 | 2019-03-30 | 2019-03-16 | Closed
28 | Legal | Anmäl verklig huvudman to BV | H | Martin | 2021-02-01 | 2020-02-01 | 2019-02-22 | Closed
29 | IT | Transfer SIM card to private use | H | Martin | 2019-03-15 | 2019-03-31 | 2019-03-15 | Closed | No. Buy new one
30 |  | Employee insurances | H | Camilla | 2019-02-15 | 2019-02-01 | 2019-02-21 | Closed | Styrelsef- ITP Avanza - …, also advice from SHB
31 | Legal | Inaugural board meetings - sign | H | Ulf | 2019-02-13 | 2019-05-08 | 2019-05-09 | Closed | Whehn do we need to hold this? What is done?
32 | Financial | Declaration & Annual report 2019-03-31 | H | Ylva | 2019-03-27 | 2019-07-10 | 2019-07-12 | Closed
33 | Sales | Frame Agreement & Assignment Spec & Simple | M | Martin |  |  | 2019-06-26 | Closed
34 | Sales | Select CRM | L | Martin | 2019-02-23 | 2019-04-01 | 2019-02-23 | Closed | Insightly free plan
35 | Financial | Transfer expenses to Punkfrog | H | Martin | 2019-10-03 | 2019-04-01 | 2019-08-03 | Closed | Done: Office 360 [ NordVPN pay PF 21/10 2020 ], SIM, Gandhi (confused login then change billing)
36 | Sales | Instal & configure Insightly Free Plan | H | Martin | 2019-02-26 | 2019-03-31 | 2019-03-09 | Closed | Organisations, contacts, opportunities. Integrate with Gmail, Outlook
37 | Sales | Instal Insightly on iPhone | M | Martin | 2019-03-31 | 2019-04-30 | 2019-03-09 | Closed
38 | Financial | Create annual plan | H | Martin | 2019-10-03 | 2019-05-09 | 2019-05-09 | Closed | Based on Camilla's list
39 | Sales | Sign Punkfrog Agreement with ESL | H | Martin | 2019-02-24 | 2019-02-25 | 2019-04-15 | Closed
40 | Financial | Send invoice to ESL for February | H | Martin | 2019-02-24 | 2019-02-28 | 2019-02-27 | Closed | Needs date 28 Feb (next April) with 2 weeks nett before bills.
41 | Administration | Put name/logo on door | L | Martin | 2019-04-01 | 2019-05-01 | 2019-03-07 | Closed | Most comes via Kivra
42 | Financial | Decide salary/dividends Feb/March | H | Ulf | 2019-03-01 | 2019-03-20 | 2019-03-15 | Closed
43 | Financial | Read bookkeeping 101 | M | Martin | 2019-03-04 | 2019-03-31 | 2019-03-27 | Closed
44 | Financial | Instal SHB corporate app | M | Martin | 2019-02-25 |  | 2019-03-01 | Closed | Browse
45 | Financial | Login to SHB corporate site | L |  |  |  | 2019-03-01 | Closed
46 | IT | Choose host for web site - Comhem? | M | Martin | 2019-02-25 | 2019-03-31 | 2019-09-24 | Closed | Use github pages
47 | Financial | Get debit card | M | Martin | 2019-02-25 | 2019-03-07 | 2019-03-08 | Closed
48 | Financial | Transfer Gsuite to Punkfrog debit card | M | Martin | 2019-02-25 | 2019-02-25 | 2019-02-25 | Closed | 14 days free
49 | IT | Decide mailing lists | M | Martin | 2019-02-26 | 2019-02-28 | 2019-02-25 | Closed | sysadmin, sales, accounts, jobs, purchasing, enquiry@
50 | IT | Activate Kivra for Punkfrog | L | Martin | 2019-02-25 | 2019-02-26 | 2019-02-25 | Closed
51 | IT | Change password for G suite | H | Martin | 2019-02-26 | 2019-02-27 | 2019-03-01 | Closed
52 | IT | Create mailing lists | M | Martin | 2019-02-26 | 2019-02-28 | 2019-02-25 | Closed
53 | IT | Devise backup/restore procedure | L | Robert | 2019-03-01 | 2019-03-31 | 2019-05-08 | Closed
54 | IT | Create free corporate Slack account | M | Martin | 2019-02-26 | 2019-02-28 | 2019-04-14 | Closed | Document operations manual slack.com free
55 | IT | Create file structure in Gdrive using web | M | Martin | 2019-02-26 | 2019-02-28 | 2019-10-03 | Closed | Cannot use file stream until leave ESL
56 | IT | Instal Drive Stream solution for easy Gdrive access | H | Martin | 2019-02-27 | 2019-04-01 | 2019-03-15 | Closed | Remove spurious files. Wait until remove ESL.
57 | IT | Change G suite user to sysadmin | L | Martin | 2019-02-26 | 2019-02-28 | 2019-05-08 | Closed
58 | IT | Create role users | L | Martin | 2019-02-26 | 2019-02-28 | 2019-05-08 | Closed | Change passwords
59 | IT | Switch File Stream to Punkfrog | M | Martin | 2019-10-03 | 2019-03-30 | 2019-03-29 | Closed | Remove spurious files. Wait until remove ESL.
60 | Financial | Subscribe to Visma and instal | H | Martin | 2019-03-14 | 2019-03-17 | 2019-03-16 | Closed | eAccounting
61 | Financial | Taxation planning 2018, 2019 | M | Ulf,Ylva | 2019-03-14 | 2019-03-31 | 2019-05-09 | Closed
62 | Financial | Make MOMS plan | H | Ylva | 2019-03-27 | 2019-04-30 | 2019-05-08 | Closed
63 | Financial | Connect Visma to SHB | M | Ylva | 2019-05-02 | 2019-05-31 | 2019-05-08 | Closed | Activate from Visma with WiFi
64 | Financial | Order company stamps | M | Martin | 2019-03-14 | 2019-05-31 | 2019-06-05 | Closed
65 | Financial | Replace debit card with credit card | L | Ylva | 2019-03-27 |  | 2019-05-08 | Closed
66 | Financial | Look at how NFT use Visma | H | Ulf | 2019-03-14 | 2019-03-22 | 2019-04-01 | Closed
67 | Financial | Buy laptop | H | Martin | 2019-03-15 | 2019-03-30 | 2019-03-16 | Closed
68 | Financial | Buy Telia subscription | H | Martin | 2019-03-16 | 2019-03-19 | 2019-03-16 | Closed | Create customer account
69 | Financial | Create sales invoices all orders | M | Martin |  |  | 2019-04-01 | Closed | Need to set up articles first
70 | Financial | Do I need Visma Decl/Annrep? | M | Ylva | 2019-03-27 | 2019-03-28 | 2019-05-08 | Closed | Not until the company grows
71 | Financial | Get Visma Acccounting and Time reset!!! | H | Martin | 2019-03-16 | 2019-03-18 | 2019-03-18 | Closed | Chat/call
72 | Financial | Configurations and settings | H | Ylva | 2019-03-18 | 2019-03-22 | 2019-03-23 | Closed | Change phone, enable two-step. Add users. Settings.
73 | Financial | Enter all current suppliers, customers | H | Martin | 2019-03-18 | 2019-03-22 | 2019-03-18 | Closed
74 | Financial | Update all contacts & BankID w phone number | H | Martin | 2019-05-08 | 2019-05-15 | 2019-06-30 | Closed
75 | IT | Fetch iPhone | H | Martin | 2019-03-19 | 2019-03-19 | 2019-03-19 | Closed
76 | IT | Fetch SIM | M | Martin | 2019-03-19 | 2019-03-19 | 2019-03-30 | Closed
77 | IT | Activate all apps iPhone & backup | M | Martin | 2019-03-20 | 2019-04-01 | 2019-04-01 | Closed
78 | IT | Separate ESL and PF phones | M | Martin |  |  | 2019-03-30 | Closed
79 | IT | Fetch laptop | M | Martin | 2019-03-25 | 2019-03-25 | 2019-03-30 | Closed
80 | IT | Migrate to new laptop and erase old | L | Martin |  |  | 2019-03-31 | Closed | Can use File Stream for Punkfrog and Web for ESL :)
81 | Financial | Create PO and Purchase Invoices for all purchases | M | Ylva |  | 2019-04-16 | 2019-04-14 | Closed | Have created PO register to tie to invoices, ok?
82 | Financial | When did f-skatt report need to start? Feb --> 12/3? | H | Ylva |  |  | 2019-05-08 | Closed | Salaries back Feb, March 63.000.
83 | Financial | Log onto tax account at SV | M | Martin |  |  | 2019-04-01 | Closed
84 | Financial | Set up payslip. Create first payslips | H | Ylva | 2019-03-25 | 2019-03-28 | 2019-04-16 | Closed | Should I buy this later?
85 | Legal | Investigate G Doc Sign extension |  |  |  |  | 2019-05-08 | Closed
86 | Insurance | Change subscription at Unionen | H | Martin | 2019-03-25 | 2019-05-31 | 2019-05-18 | Closed
87 |  | Migrate Outlook DB for ownit | M | Martin | 2019-03-25 |  | 2019-04-14 | Closed | Import contacts & email; Sync contacts to iPhone
88 |  | Migrate/test Garageband files | L | Martin | 2019-05-08 | 2019-06-30 | 2019-06-17 | Closed
89 |  | Migrate iTunes media | M | Martin | 2019-05-08 | 2019-06-30 | 2019-06-06 | Closed | All albums complete and correct?
90 |  | Migrate iMovie projects | L | Martin | 2019-05-08 | 2019-06-30 | 2019-06-17 | Closed
91 | Financial | Change SHB Visa 2SV phone number | M | Martin | 2019-04-13 | 2019-05-30 | 2019-04-15 | Closed | Connected to private account
92 | Administration | Create presentation template | L | Martin | 2019-04-22 | 2019-05-31 | 2019-07-21 | Closed
93 | Marketing | Complete Linkedin page | M | Martin | 2019-04-28 | 2019-05-31 | 2019-12-20 | Closed | Cancelled
94 | Marketing | Ask for endorsements | L | Martin | 2019-05-01 | 2019-12-31 | 2019-12-20 | Closed | Cancelled
95 | Marketing | Order stickers | H | Martin | 2019-05-02 | 2019-05-14 | 2019-05-09 | Closed | visitkort.se for CBSTO
96 | HR | Employment contracts kill-eat | H | Martin | 2019-05-01 | 2019-07-01 | 2019-08-16 | Closed | Get from Sylog with spreadsheet
97 | Financial | Plan annual/month & routines | H | Martin | 2019-05-09 | 2019-08-13 | 2019-11-05 | Closed
98 | Financial | Cashflow forecast | M | Martin | 2019-05-13 | 2019-08-13 | 2019-12-18 | Closed | Will be unpredictable; month target
99 | Administration | Decide final template colour & update | H | Martin | 2019-05-08 | 2019-05-31 | 2019-05-09 | Closed
100 | Financial | Pensionsförsäkring | H | Martin | 2019-05-18 | 2019-08-12 | 2019-08-15 | Closed | Soderbergs. Do policy when employ.
101 | Administration | Evaluate Gdoc sign extension | M | Martin | 2019-06-06 | 2019-06-14 | 2019-06-15 | Closed
102 | Financial | Set salary to 42K or 60K | H | Martin | 2019-05-18 | 2019-05-23 | 2019-05-25 | Closed
103 | HR | Change from private to corporate Unionen | H | Martin | 2019-05-18 | 2019-05-24 | 2019-05-21 | Closed | Private membership & Bliwa
104 | HR | Företagsförsäkring FOLKSAM | H | Martin | 2019-05-18 | 2019-05-24 | 2019-05-24 | Closed | Quote 20% discount, turnover.
105 | Marketing | Brainstorm share with Maja | H | Martin | 2019-05-27 | 2019-06-30 | 2019-05-28 | Closed
106 | Financial | Apply for invoicing at EspressoHouse | H | Martin | 2019-05-28 | 2019-06-04 | 2019-05-29 | Closed
107 | Sales | Sell Per | H | Martin | 2019-06-01 | 2019-07-31 | 2019-08-30 | Closed | Failed. Perhaps mentoring at Sigicom
108 | Sales | Find more consultants | M | Martin | 2019-07-01 | 2019-09-30 | 2019-08-24 | Closed | Slagskeppet, Sylog
109 | Governance | Template board meeting | H | Martin | 2019-07-21 | 2019-07-26 | 2019-07-21 | Closed
110 | Governance | Call board meeting #2 | M | Martin | 2019-07-21 | 2019-08-15 | 2019-08-28 | Closed | Update all materials, in shared directory :) Send link
111 | HR | Template employment contract (normal) | H | Martin | 2019-07-21 | 2019-07-26 | 2019-07-30 | Closed | Compare with NFT
112 | HR | Employ Sylvana, without pensions | M | Martin | 2019-07-21 | 2019-07-31 | 2019-08-16 | Closed
113 | HR | Get TFA for all employees | M | Martin | 2019-07-21 | 2019-08-30 | 2019-09-19 | Closed | Applies after 17/9 all employees
114 | HR | Pilot onboarding checklist Sylvana | L | Martin | 2019-07-21 | 2019-08-15 | 2019-08-24 | Closed
115 | Financial | Budget 2019 | M | Martin | 2019-07-21 | 2019-09-30 | 2019-12-20 | Closed | Cancelled
116 | Governance | Affärsplan (Business Plan) 2020 | M | Martin | 2019-07-21 | 2019-08-31 | 2019-12-20 | Closed | Cancelled
117 | Governance | Prepare Board meeting #2 | M | Martin | 2019-07-21 | 2019-08-15 | 2019-07-24 | Closed
118 | Financial | Calculate insurance premiums in staff register | L | Martin | 2019-07-21 | 2019-12-31 | 2019-12-20 | Closed | Cancelled
119 | HR | Set up recruitment process | M | Martin | 2019-07-21 | 2019-07-31 | 2019-07-22 | Closed
120 | HR | Add technical task evaluation to process | M | Martin | 2019-07-22 | 2019-07-31 | 2019-07-22 | Closed
121 | HR | Find technical evaluation guidelines | L | Martin | 2019-07-22 | 2019-07-31 | 2019-12-20 | Closed
122 | Financial | Buy assets into company | H | Martin | 2019-07-25 | 2019-08-13 | 2019-08-20 | Closed
123 | HR | GDPR Applicant Privacy Notice | H | Martin | 2019-07-30 | 2019-07-30 | 2019-07-30 | Closed
124 | HR | Derive language proficiency charts per consultant | H | Martin | 2019-08-07 | 2019-08-15 | 2019-08-08 | Closed
125 | Financial | Budget costs & revenue driven by headcount | M | Martin | 2019-08-18 | 2019-09-01 | 2019-08-23 | Closed
126 | HR | Review employment contract & conditions | M | Martin | 2019-08-24 | 2019-12-31 | 2019-12-20 | Closed
127 | HR | Interview Robert G | H | Martin | 2019-09-01 | 2019-09-10 | 2019-09-10 | Closed | He needs to wait maybe 2020
128 | HR | Book break-up party | H | Sylvana | 2019-09-08 | 2019-09-22 | 2019-10-20 | Closed | Martin, Sylvana, Ulf, Ewa/Camilla
129 | Sales | Scope business ideas Energy Machines | M | Martin | 2019-09-14 | 2019-09-22 | 2019-12-20 | Closed | E/// outsource; RISE IoT; etc
130 | HR | Complete profile for Jia | M | Martin | 2019-09-10 | 2019-09-30 | 2019-09-16 | Closed | Sell for Jan/Feb
131 | Sales | Create RabbitMQ services. Contact customners | M | Martin | 2019-09-14 | 2019-10-25 | 2019-11-04 | Closed | ascom 25/10 (xperi, insta, leoVegas, 84codes)
132 | HR | Interview Daniel | M | Martin | 2019-09-03 | 2019-09-15 | 2019-09-12 | Closed
133 | HR | Interview Kristian | H | Martin | 2019-09-03 | 2019-09-15 | 2019-09-14 | Closed
134 | Sales | Add and scope work for Kristian | H | Martin | 2019-09-14 | 2019-09-21 | 2019-12-20 | Closed
135 | Marketing | Create placemarker landing page | H | Martin | 1900-01-19 21:36 | 2019-09-29 | 2019-09-29 | Closed
136 | Marketing | Fix site security https://www.punkfrog.se | M | Martin | 2019-10-01 | 2019-12-31 | 2019-12-20 | Closed | Cancelled
137 | HR | Update profiles with new languages | M | Martin | 2019-10-19 | 2019-10-31 | 2019-10-23 | Closed | Jia, Per
138 | Financial | Check and approve tex return | M | Martin | 2019-09-01 | 2019-11-30 | 2019-11-30 | Closed
139 | Financial | Create PO for all back purchases | L | Martin | 2019-10-20 | 2019-12-31 | 2019-12-27 | Closed | Cancelled
140 | Sales | Buy a clicker | M | Martin | 2019-10-20 | 2019-11-30 | 2019-10-31 | Closed
141 | Administration | Change address on all templates | M | Martin | 2019-10-20 | 2019-10-31 | 2019-10-21 | Closed
142 | Financial | Change address BV, adressänring for myndigeter | M | Martin | 2019-11-03 | 2019-11-30 | 2019-11-02 | Closed
143 | HR | Activate Mikael Karlsson - interview | H | Martin | 2019-10-24 | 2019-10-31 | 2019-10-30 | Closed
144 | Administration | Order new office stamp(s) | M | Martin | 2019-10-24 | 2019-11-30 | 2019-11-02 | Closed
145 | Administration | Find out move in date | H | Martin | 2019-10-25 | 2019-11-08 | 2019-11-04 | Closed | Delivereies
146 | Administration | Order furniture | M | Martin | 2019-04-18 | 2019-11-24 | 2019-11-28 | Closed | Set up invoicing, and do PO first.
147 | Financial | Notify change of address all vendors/customers/contractors | M | Martin | 2019-11-02 | 2019-11-30 | 2019-11-02 | Closed | Customers done.
148 | Administration | Check allabolag has address, and google maps | L | Martin | 2019-12-01 | 2019-12-15 | 2019-12-20 | Closed | changed gmaps manually. 7/12 belum
149 | Financial | Get refund from TotalAV | M | Martin | 2019-11-03 | 2019-11-30 | 2019-12-19 | Closed
150 | Security | Replace ownit.nu with Gmail. Set security levels on all Gmail accounts. Thunderbird encryption. | L | Martin | 2019-11-03 | 2019-12-31 | 2019-12-27 | Closed | Certificate
151 | Administration | Thunderbird email footers | M | Martin | 2019-11-03 | 2019-11-08 | 2019-11-04 | Closed
152 | Administration | Thunderbird calendars | H | Martin | 2019-11-03 | 2019-11-08 | 2019-11-04 | Closed
153 | Administration | Thunderbird outlook archives | H | Martin | 2019-11-03 | 2019-11-30 | 2019-11-05 | Closed | Outlook OML. Convert to MBOX.
154 | Administration | Thunderbird coloured emails | L | Martin | 2019-11-03 | 2019-11-08 | 2019-11-06 | Closed | Waiting for account-colors 68.2.1 (v12.0)
155 | Administration | Thunderbird contacts - how synchronised? | M | Martin | 2019-11-03 | 2019-12-31 | 2019-11-05 | Closed | Turn off use OSX then add again
156 | Administration | Create handbook based on UMA office | M | Martin | 2019-11-29 | 2019-12-03 | 2019-12-18 | Closed | Started, awaiting answers from UMA.
157 | Administration | Test printer, get keys --> asset register | M | Martin | 2019-12-03 | 2019-12-03 | 2020-01-01 | Closed | Cancelled
158 | Adminsitration | Create door sign | M | Martin | 2019-11-29 | 2019-12-15 | 2020-01-01 | Closed | Cancelled
159 | HR | Recruit Henry | M | Martin | 2019-12-05 | 2019-12-31 | 2019-12-18 | Closed | 3 months' notice
160 | Product | Create and print refills | H | Martin | 2019-12-01 | 2019-12-31 | 2020-01-01 | Closed | Cancelled
161 | Product | Specify mEdison for KYH project | M | Martin | 2019-12-01 | 2020-01-31 | 2020-01-01 | Closed | Cancelled
162 | Financial | Define Articles for Internal time | L | Martin | 2019-12-19 | 2020-03-31 | 2019-12-18 | Closed | Cancelled
163 | Administration | Sign minutes from board meeting #3 | M | Ulf | 2019-12-19 | 2019-12-20 | 2020-01-01 | Closed | Cancelled
164 | Administration | Update hourly rate in Jia's contract | L | Martin | 2019-12-19 | 2020-01-30 | 2020-01-01 | Closed | Cancelled
165 | Product | Create services: 7MT-RCA | H | Martin | 2019-12-19 | 2020-01-15 | 2020-01-01 | Closed | Cancelled
166 | Sales | Sales collateral for 7MT-RCA | H | Martin | 2019-12-19 | 2020-01-15 | 2020-01-01 | Closed | Cancelled
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))

## PF-2020 (hidden)
Date: | 2026-03-06 | Punkfrog Management
# | Initiative | Decision/Action | Prio | Assigned | Start date | Due Date | Closed Date | Status | Comments
1 | Marketing | Create website | H | Kristian | 2020-01-01 | 2020-07-15 |  | Due
2 | Marketing | Complete Linkedin page | L | Martin | 2020-01-01 | 2020-07-30 |  | Due
3 | Marketing | Ask for endorsements | L | Martin | 2020-01-01 | 2020-07-31 |  | Due | Seeqest
4 | Financial | Budget 2019 | M | Martin | 2020-01-01 | 2020-03-12 | 2020-03-19 | Closed | Styrelsemöte 23/3
5 | Governance | Affärsplan (Business Plan) 2020 | M | Martin | 2020-01-01 | 2020-04-30 | 2020-04-12 | Closed
6 | Quality | Create google form surveys for workshops, courses, consultancy | M | Martin | 2020-01-01 | 2020-01-31 | 2020-01-11 | Closed | Support Stavros
7 | Admin | Test printer | H | UMA | 2019-12-03 | 2020-01-10 | 2020-01-09 | Closed
8 | Admin | Print door sign, refills | H | Martin | 2020-01-02 | 2020-01-10 | 2020-01-09 | Closed
9 | Admin | Update Jia's contract rate | H | Martin | 2020-01-02 | 2020-01-10 | 2020-01-03 | Closed
10 | Admin | Sign minutes from board meeting | H | Ulf | 2019-12-19 | 2020-01-10 | 2015-01-01 | Closed
11 | TP3-Rx | Specify & requirements mEDISON -> Trello | H | Martin | 2020-01-01 | 2020-03-22 | 2020-03-23 | Closed | Including milestones
12 | Sales | Sales brochure CI-7MT | H | Martin | 2019-12-19 | 2020-01-10 | 2020-01-08 | Closed
13 | CI-7MT | Create CI-7MT presentation | H | Martin | 2019-12-19 | 2020-07-31 |  | Due
14 | TP3-Rx | Create Trello product backlog | M | Martin | 2020-01-31 | 2020-02-28 | 2020-01-10 | Closed | My Trello or theirs?
15 | TP3-Rx | Create template for Project Plan | M | Martin | 2020-01-31 | 2020-02-28 | 2020-01-10 | Closed | Used after kick-off
16 | TP3-Rx | Create gsheet for bug reporting | M | Martin | 2020-01-31 | 2020-02-28 | 2020-01-10 | Closed
17 | TP3-Rx | Kick-off presentation | M | Martin | 2020-01-31 | 2020-03-22 | 2020-03-23 | Closed | Explain req & materials, timeplan, tools (projplan, trello, bugs), func v look, improvise
18 | Marketing | Prepare BLU | M | Martin | 2020-01-31 | 2020-01-31 | 2020-02-07 | Closed
19 | Marketing | Venue BLU April etc | M | Martin |  | 2020-01-31 | 2020-12-02 | Closed
20 | TP3-Rx | Prepare iOS/Android dev/test environments | H | Martin | 2020-01-02 | 2020-02-29 | 2020-02-28 | Closed | KJK
21 | TP3-Rx | Create Github project | H | Martin | 2020-01-10 | 2020-02-29 | 2020-02-28 | Closed | KJK
22 | Sales | Register as supplier to Telia via Wrokforce LogiQ | M | Martin | 2020-01-09 | 2020-01-31 | 2028-01-01 | Closed | Application completed 10/1
23 | Admin | Call and prepare board meeting | H | Martin | 2020-02-26 | 2020-03-18 | 2020-03-19 | Closed
24 | Financial | Budget 2020 | M | Martin | 2020-04-01 | 2020-05-31 | 2020-04-15 | Closed | Need to close FY2019 first
25 | Operations | Increase Martin's health insurance (S&P) | M | Martin | 2020-04-24 | 2020-06-30 |  | Due | Requested David
26 | Operations | GDPR: Data Processing Agreement template | [5 empty] | -
27 |  | GDPR: Data Processing Agreements with suppliers | [5 empty] | -
28 |  | GDPR: Data Processing Register | [5 empty] | -
29 |  | GDPR: Privacy Policy | H | Martin | 2020-03-26 | 2020-03-31 | 2020-03-28 | Closed
30 |  | GDPR: procedures | [5 empty] | -
31 |  | GDPR: Data Breach Log | [5 empty] | -
32 |  | GDPR: Information Asset Register (IAR) | M | Martin | 2020-03-26 | 2020-03-31 |  | Due
33 |  | GDPR: Record of Consent | M | Martin | 2020-03-26 | 2020-03-31 | 2020-04-03 | Closed
34 | HR | Staff shirts printing for Code BEAM STO | M | Martin | 2020-06-30 | 2020-12-31 |  | Due
35 | Product | Complete dosR specification | H | Martin | 2020-02-01 | 2020-04-05 | 2020-04-21 | Closed
36 | Product | Translate dosR content to Swedish | M | Martin | 2020-04-05 | 2020-04-30 | 2020-04-27 | Closed
37 | HR | Create General Terms and split the Service Agreement and Contractor Agreement, according to legal review. | H | Martin | 2020-04-04 | 2020-04-30 |  | Due
38 | Quality | Create Boomerang Consultancy Survey | H | Martin | 2020-04-04 | 2020-04-05 | 2020-04-08 | Closed
39 | Quality | Send survey to Faria | M | Martin | 2020-04-04 | 2020-04-13 | 2020-04-08 | Closed
40 | Financial | Get record of shares from Seeqest, and book into accounts | H | Martin | 2020-01-01 | 2020-06-01 | 2020-07-30 | Closed | 1/6 status sent to BV, then we need to be offered and buy them
41 | Financial | Close FY2019 | H | Martin | 2020-04-01 | 2020-04-30 | 2020-05-18 | Closed
42 | Financial | Budget 2020 --> Business Plan targets | M | Martin | 2020-04-13 | 2020-05-15 | 2020-05-21 | Closed
43 | Financial | Finalise Business plan | M | Martin | 2020-04-13 | 2020-05-15 | 2020-05-18 | Closed
44 | Financial | Terminate Telia 2021-03-27. | M | Martin | 2020-05-20 | 2020-11-06 | 2020-12-03 | Closed
45 | Financial | Move family to Punkfrog Hallon | H | Martin | 2020-05-20 | 2020-06-01 | 2020-06-01 | Closed | R ok, S 29/5, W 1/6
46 | Financial | Create budget V actual report | H | <artin | 2020-05-23 | 2020-05-31 | 2020-05-24 | Closed
47 | Admin | Generate and print planR 2021 | M | Martin | 2020-06-02 | 2020-07-31 | 2020-06-04 | Closed | Before I leave UMA
48 | Admin | Cut planR 2020H2 | H | Martin | 2020-06-02 | 2020-06-30 | 2020-06-04 | Closed
49 | HR | Artwork for shirts | H | Martin | 2020-03-30 | 2020-06-30 | 2020-07-03 | Closed
50 | Product | Build dosR prototype | M | Martin | 2020-06-01 | 2020-10-31 |  | Due | Start with BA in Cradle. K Larberg as intern Nov-Mar?
51 | Financial | Avstämning: reporting hours 1/4 - 30/6 | M | Martin | 2020-07-01 | 2020-07-14 | 2020-07-03 | Closed | https://tillvaxtverket.se/veta
52 | Financial | Apply for extension, 80% furlough | M | Martin | 2020-07-14 | 2020-07-31 | 2020-07-03 | Closed
53 | Quality | Create staff/contractor survey | M | Martin | 2020-06-15 | 2020-06-30 | 2020-06-21 | Closed
54 | HR | Survey staff satisfaction | M | Martin | 2020-06-01 | 2020-06-30 | 2020-06-24 | Closed | Brett, Jia, Mikael, Jonas, Henry
55 | Financial | Time reporting shows too many articles. Staff should only see what they are allocated. Period. | H | Martin | 2020-06-23 |  |  | - | Contact Visma for improvement. Make all unused articles inactive. Use same rate, with discounts.
56 | Sales | Survey customer satisfation | H | Martin | 2020-06-01 | 2020-06-30 | 2020-06-30 | Closed | Faria
57 | Admin | New security door at a home office | H | Martin | 2020-06-20 | 2020-07-31 | 2020-09-01 | Closed
58 | Admin | planR annual overview | L | Martin | 2020-07-01 | 2020-12-01 | 2020-07-03 | Closed
59 | Admin | Sound-proofing balcony at home office | H | Martin | 2020-06-01 | 2020-11-30 | 2020-10-02 | Closed
60 | Financial | Track metrics monthly/quarterly | M | Martin | 2020-07-01 | 2020-08-31 | 2020-07-08 | Closed
61 | Quality | Refactor planR code | L | Martin | 2020-07-29 | 2020-12-31 |  | Due
62 | Product | Get patent application | M | Ulf | 2020-07-01 | 2020-08-28 |  | Due
63 | Operations | Cradle: set screen resolution | M | Martin | 2020-08-16 | 2020-08-31 | 2020-09-01 | Closed
64 | Operations | Cradle: share folder Ubuntu/OSX or print from Ubuntu/VM | M | Martin | 2020-08-16 | 2020-08-31 |  | Due | Can print directly from Cradle?
65 | Operations | Filing agent for Redfin | H | Martin | 2020-08-19 | 2020-08-31 | 2020-11-06 | Closed | SBS, Freddy
66 | Product | Create product process with milestones | M | Martin | 2020-08-22 | 2020-10-30 |  | Due
67 | Product | Get CBAP certification | H | Martin | 2020-07-26 | 2020-09-15 | 2020-09-10 | Closed | Course; schedule; exam
68 | Product | Study git/github | M | Martin | 2020-09-04 | 2020-12-31 | 2020-09-22 | Closed
69 | Product | Study at university | H | Martin | 2020-09-04 | 2020-12-31 |  | Due | Register eligibility
70 | Admin | Remove Henry duplicate from time reporting | L | Martin | 2020-09-18 | 2020-12-31 | 2020-12-18 | Closed | Reported to help desk
71 | Admin | Plan office move & order furniture | M | Martin | 2020-10-01 | 2020-11-30 | 2020-12-28 | Closed
72 | Sales | Regular meetings with customers | [5 empty] | -
73 | Sales | Extend range of assignments with agents | H | Martin | 2020-09-18 | 2020-11-30 | 2020-10-02 | Closed | Added SV, Postnord, AssaAblot at WFQ - extended range at Telia, FP at Tingent
74 | HR | Give Kristoffer Larberg recommendation, based on creative brief, and release some screens | L | Martin | 2020-10-01 | 2020-10-16 | 2020-10-12 | Closed | He did style guide. Flutter library for localisation. Any screen content?
75 | Dev | Clean up git and github - one location. Not public? | L | Kristian | 2020-09-18 | 2020-10-31 |  | Due | Martin/Development/flutter /Documents/Punkfrog/Dev/dosR/ /local-dev/punkfrogab.github.io
76 | Operations | Transition from Gsuite to Google Workspace | M | Martin | 2020-10-08 | 2020-10-31 | 2020-10-08 | Closed
77 | Admin | Print/cut planR 2021 | M | Martin | 2020-10-19 | 2020-11-30 | 2020-11-05 | Closed
78 | Admin | Decide and book xmas dinner | H | Martin | 2020-10-19 | 2020-11-05 | 2020-11-05 | Closed
79 | HR | Update profiles | M | Martin | 2020-11-01 | 2020-12-15 | 2020-11-26 | Closed | Henry, (Jonas), (Mikael). Done: Robin, Per, Jia, Daniel
80 | HR | Utvecklingssamtal | M | Martin | 2020-11-15 | 2020-12-15 | 2020-11-23 | Closed | Status, ambition, profile. (JB) Done: Henry, Jia.
81 | Product | Titles/topics for webinars/meettups | L |  |  |  |  | -
82 | Product | Complete annexes for service agreement | L |  |  |  |  | -
83 | Product | Rip 5.25" diskettes in London | L |  |  |  |  | -
84 | Product | Contact CGI for source code A/D Toolkit | [5 empty] | -
85 | Product | Retrofit HP25C | M |  |  |  |  | -
86 | Marketing | Cinema tickets | L |  |  |  |  | -
87 | Admin | Loudspeakers for webinars | L |  |  |  |  | -
88 | Product | Fix dosR (update) | [5 empty] | - | Pay someone to teach me how :)
89 | Financial | Subscribe Hallon 25GB = 149kr, port number 2021-03-29 | M | Martin | 2020-12-03 | 2020-12-31 | 2020-12-04 | Closed
90 | HR | Clarify Jia feedback with Mattis call | M | Martin | 2020-12-18 | 2020-12-11 | 2020-12-11 | Closed
91 | HR | Why droppd score with Jia? | M | Martin | 2020-12-16 | 2020-12-15 | 2020-12-11 | Closed
92 | System admin | Purge KeepAssXC when able to drag & drop entries | L | Martin | 2020-12-14 | 2021-01-31 |  | Due
93 | Sales | Convert and update brag book. | M | Martin | 2021-01-07 | 2021-06-30 |  | Due | Endorsement Wim. Latest copies. Update qualifications. Renoir, ESL, Punkfrog. Digital (index) and can print.
94 | [7 empty] | -
95 | [7 empty] | -
96 | [7 empty] | -
97 | [7 empty] | -
98 | [7 empty] | -
99 | [7 empty] | -
100 | [7 empty] | -
101 | [7 empty] | -
Unscheduled ideas
Specify scope for Training & RabbitMQ services
Effective meetings
Upgrade Gsuite (Basic $6/user) --> Business ($12/user) when want to use shared drives.
Backup/restore procedure
Extnd Visma with Payroll, Reporting when PF grows
Calculate insurance premiums in staff register
Define Articles for Internal time
Employ --> Customised emplyment T&C
Outsource HR (custom terms, accounting/payroll, pension policy)
Pension policy defined by S&P
Replace ownit.nu with Gmail. Set security levels on all Gmail accounts. Thunderbird encryption.
Create PO for all back purchases
Fix site security https://www.punkfrog.se (with new website!)
Review employment contract & conditions
Formulas:
Status = IF(AND([Due Date]="",[Closed Date]=""),"-",IF(AND([Closed Date]="",TODAY()>=[Due Date]),"Due",IF(AND([Closed Date]="",TODAY()<[Due Date]),"Open","Closed")))