## Instructions
RACI - Responsibility Chart |  | PF/O-26:003 2026-03-06 version 1.0.1
A clear framework for assigning roles and accountability.
Introduction
In 1988, I read "Målinriktad projektstyrning (Goal Directed Project Management)". The book's main premise is that you can plan everything in detail, but if no-one reads it or uses it, then it is a waste of time. Instead, the authors identify the absolute minimum of three documents required to control a project: Milestone Plan, Activity Plan, and Responsibility Chart.
The Responsibility Chart is most often called a "RACI" based on the four symbols used to denote roles within a project: "R" - Responsible, "A" - Accountable, "C" - Consulted, and "I" - Informed.
This document provides a flexible template with instructions how to use it; it is not meant to be a guide for how to create a RACI. There is a plethora of information readily available, but I can recommend these:-
| • The RACI Model, https:racichart.org/project | Basic orientation and understanding.
| • "Goal Directed Project Management", Andersen, Grude, and Haug. | Detailed, practical advice how to use the RACI effectively, and avoid pitfalls.
Description
The template under the sheet named "RACI" has been designed flexibly to manage a large project consisting of several sub-projects, and multiple groups of stakeholders who have key roles in the project.
• For simpler projects, delete unnecessary parts, or hide them if you might need them later.
• For larger projects, add rows, columns, groups of stakeholders, or sub-projects as necessary.
• When you write "AR", "A", "R", "C", or "I" into the chart cells, they are conditionally formatted to highlight the key roles Accountable and Responsible.
• Sections of information are grouped so they can be collapsed, and support focus on one area at a time.
• Note that grouped data in Excel collapses down to it's heading. This is because Excel is a spreadsheet, and this function is used to hide detail and show the sum of a column. This means that section "Headings" are actually "Footings".
Using the RACI Responsibility Chart
It is recommended to populate the fields in the chart in the following order:-
Title | Description | Usage
PROJECT | Name of the highest level of the project or area which needs to be organised, in order for all key stakeholders to understand their roles. | If the project name is random like "Dynamo Project", consider including a tag line which explains for everyone what it is about.
SUB-PROJECT | If the PROJECT is large enough, or already organised that way, name the SUB-PROJECTS. | • Fill in in left field, not the middle one. • If the sub-projects are called "Red", "White" and "Blue", not all stakeholders may understand. Consider using self-explanatory terms (e.g. Requirements [red], Coding [white], Testing [blue]).
MAJOR TASK | As for a project Gantt chart, define the MAJOR TASKS for each SUB-PROJECT. | Not all tasks - just the major ones necessary to assure control over the project.
Key activity | List each KEY ACTIVITY for each MAJOR TASK. | Not all activities - just the key activities necessary to assure control over the project. Sometimes, small activities can be very important.
REMARKS |  | Use only if more clarification is necessary to avoid misinterpretation. Don't add new information which changes the meaning of the activity.
STAKEHOLDER | This is a grouping name used to gather roles and people from a particular function. | Divisions, departments (e.g. Legal, Sales, Operations).
Generic role | A person in the organisation who is directly involved in the PROJECT. | Start by naming a generic role (e.g. PM), and later naming the actual person involved. If not every knows who Sarah is, name the role PM - Sarah C.
RACI body | R - Responsible: the person responsible for completing or implementing the task. A - Accountable: the person with the authority and ability to say "yes" or "no", making them ultimately accountable for the success or failure of the task. C - Consulted: any person who must be consulted prior to taking a final decision or action. I - Informed: any person who must be informed after decisions or actions are taken so that they may fulfil their duties. | R - there must be one, and only one "R" associated with each activity. If several people are actually doing the work, one must be responsible for the others (e.g. PM). A - there can be zero or one "A" for an activity. Not all activities are significant enough to need someone accountable; use "A" only when it is important to know. C - can be multiple for an activity. Note it is not "was" or "can", but "must" be consulted, or the decision will not be valid. I - can be multiple for an activity. It doesn't mean everyone in the project that will hear this at a meeting, but those who "must" be informed of the decision/action.
Metrics
METRICS (footer) | Automated filed for all rows in current chart. | See how loaded each role is.
METRICS (right) | Automatded filled for all columns in current chart. | See if a task has conflicting roles (e.g. A >1), R is missing or >1

## RACI
Responsibility Matrix (RACI) | [27 empty] | METRICS
R A C I | Responsible Accountable must be Consulted must be Informed | PROJECT | [24 empty] | REMARKS | Accountable & Responsible | Accountable | Responsible | must be Consulted | must be Informed
|  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 | [6 empty] | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible
|  | STAKEHOLDER |  |  |  |  | STAKEHOLDER |  |  |  |  | STAKEHOLDER |  |  |  |  | STAKEHOLDER |  |  |  |  | STAKEHOLDER | [6 empty] | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible
|  | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role | Generic role |  |  | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible | Accountable and Responsible
1-1-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-1-2 | Key activity |  |  | A |  | R | AR | C | I |  | A | [16 empty] | 1 | 2 | 1 | 1 | 1
1-1-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-1-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-1 | MAJOR TASK | MAJOR TASK
1-2-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-2-2 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-2-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-2-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-2 | MAJOR TASK | MAJOR TASK
1-3-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-3-2 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-3-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-3-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
1-3 | MAJOR TASK | MAJOR TASK
1 | SUB-PROJECT | SUB-PROJECT
2-1-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-1-2 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-1-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-1-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-1 | MAJOR TASK | MAJOR TASK
2-2-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-2-2 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-2-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-2-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-2 | MAJOR TASK | MAJOR TASK
2-3-1 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-3-2 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-3-3 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-3-4 | Key activity | [26 empty] | 0 | 0 | 0 | 0 | 0
2-3 | MAJOR TASK | MAJOR TASK
2 | SUB-PROJECT | SUB-PROJECT
METRICS | Accountable & Responsible | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accountable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Responsible | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| must be Consulted | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| must be Informed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0